Fubon Bank Hong Kong

CMG CRMS - Weekly Sync-up

| Date & Time | 11 Sep 2026 16:00 - 16:30 |
| --- | --- |
| Attendee (Fubon CMG) | Kay Law, Eddy Yuen, Warren Ng, Beatrice Cheng |
| Attendee (Fubon IT) | Elvis You, Cindy Chan, Windy Yeung, Trevor Wong |
| Attendee (Deloitte) | Steven Leong, James Wong, Paco Tsang, Jeffrey Tang, Gavin Ding |

Project Status & Schedule Alignment

- [Steven]: Confirmed overall project status remains Green across Scope, Schedule, and Budget.

- [Steven]: Announced key upcoming schedule and milestones:

  - Sprint 3 Show & Tell: Scheduled for 21/09.

  - Technical Go-Live / Deployment: Targeted for 02/11 – 06/11.

  - Pilot Phase (Champion Users): Scheduled for 10/11 – 20/11.

  - Business Go-Live & Deployment: Targeted for 25/11.

Deployment & Environment Clarifications

- [Kay]: Requested clarification on the definition of Technical Go-Live.

  - [Steven]: Clarified that following Technical Go-Live, pilot users will be aligned to use the platform, with UAT completed prior to the pilot phase.

- [James]: Explained that production data will be used in the production environment during the pilot phase, with dedicated IT support provided while restricting direct data manipulation.

UAT Planning, Review & Sign-Off Criteria

- [Steven]: Outlined the UAT preparation and review schedule:

  - Internal SIT Testing: Deloitte will complete SIT test cases internally prior to UAT.

  - 22/09: Target date to send UAT test cases to CMG categorized by user roles.

  - 22/09 – 29/09: CMG review period for process flows and test cases.

  - 30/09 – 02/10: CMG to confirm and finalize UAT test cases.

- [Steven]: Proposed holding an on-site, guided UAT session.

- [Steven]: Defined UAT sign-off criteria:

  - Requires formal sign-off approval from Jeff.

  - Requires a passing rate of 90% or higher with zero open critical issues.

- [Kay]: Noted that team members have limited implementation experience and requested extra time and guidance for explaining test case severity (e.g., defining critical test cases).

Defect Logging & Triage Process

- [Kay]: Inquired about the procedure and tool for logging UAT test cases and defects.

  - [Steven]: Confirmed Fubon internal logging systems will not be used; defects will be tracked via a standard Excel template where users record severity, issue details, and screenshots.

  - [Steven]: Confirmed daily triage sync-up calls will be held to verbally walk through reported defects.

  - [Steven]: Noted that Deloitte is investigating version control management for the Excel tracker.

  - [Steven]: Reassured CMG that all critical issues will be resolved prior to rollout.

Test User Nomination & Access

- [Steven]: Requested CMG to nominate test users for each role, providing full names and email addresses.

- [Kay]: Noted a preference for operational team members to test rather than Department or Division Heads testing directly.

Data Upload Functionality & Role Alignment

- [Paco]: Inquired regarding responsibility for Account List, Actual vs. Target, and Call Report target uploads.

  - [Paco]: Noted that Actual vs. Target data currently originates from manual EDP uploads, and CIF call targets can be updated at any time.

  - [Paco]: Confirmed multiple users can be authorized to perform uploads.

- [Kay]: Confirmed I will finalize the assigned upload roles (likely Team Heads or RMs).

Action Items

- Deloitte - Conduct Sprint 3 Show & Tell on 21/09.

- Kay – Provide endorsement for the UAT Test plan by 18/09.

- Kay - Submit test user nominations (names and emails) per role to Deloitte. By 18/09

- Deloitte – Provision of  role-based UAT test cases by 22/09.

- Deloitte – Schedule a Test Case walk-through meeting with business users on 22/09

- Deloitte - Explore version control process for Excel defect tracking with ITG by 14/09

- CMG - Review UAT test cases and finalize confirmation by 02/10.

- Kay - Finalize and confirm user role assignments for Account List and Call Report target uploads. By 16/09