Fubon Bank Hong Kong

CMG CRMS - Weekly Sync-up

| Date & Time | 18 Sep 2026 16:00 - 16:30 |
| --- | --- |
| Attendee (Fubon CMG) | Kay Law, Eddy Yuen, Warren Ng, Bonnie Kwan, Bryan Cheung, Carman Lai |
| Attendee (Fubon IT) | Cindy Chan, Trevor Wong, Penny Tse |
| Attendee (Deloitte) | Steven Leong, James Wong, Paco Tsang, Jeffrey Tang, Gavin Ding |

Project Status & Schedule Alignment

- [Steven]: Confirmed overall project status remains Green across Scope, Schedule, and Budget.

- [Steven]: Announced key upcoming schedule and milestones:

  - 2A Sprint 3 Show & Tell: Scheduled for 21/09.

  - Technical Go-Live / Deployment: Targeted for 02/11 – 06/11.

  - Pilot Phase (Champion Users): Scheduled for 10/11 – 20/11.

  - Business Go-Live & Deployment: Targeted for 25/11.

Account Renewal Alert Alignment

- [Steven]: Inquired if additional fields are required for the account renewal alert.

  - [Kay]: Explained regular annual review frequency based on risk rating:

    - High Risk: Annual review.

    - Medium Risk: Review every 3–5 years.

    - Low Risk: Review every 10 years (occasional ad-hoc review required).

  - [Paco]: Inquired whether renewal dates reside in Finacle.

  - [Kay]: Confirmed Finacle data and reporting logic:

    - Finacle Data: Tracks last review dates and risk ratings, triggering alerts 90 days prior to regular reviews.

    - Legacy Gaps: Identified issues in Mobius and AML 070 reports where ad-hoc reviews or risk updates failed to sync,erroneously flagging accounts as pending follow-up.

  - [Cindy]: Requested Kay to share the internal regular review alert report, which Kay agreed to provide.

- [Eddy]: Noted that ad-hoc reviews exist separately from regular reviews.

  - [Kay]: Inquired whether showing only regular review alerts in CRM while omitting ad-hoc alerts would cause confusion.

  - [James]: Clarified three current call report types: annual review, merchant site-visit, and e-commerce review.

  - [Bryan]: Explained ad-hoc reviews (e.g., client management changes or account reactivation) reset the next regular review date, turning it into a moving target.

  - [Cindy]: Confirmed using Finacle data (risk rating and last review date) to calculate next regular review dates.

- [Steven]: Noted that major requirement changes could impact project timelines and move features to Phase 3.

- [Paco]: Asked if key information beyond 90-day alerts is needed.

  - [Kay]: Confirmed alerting users is sufficient.

UAT Preparation & Schedule

- [Steven]: Outlined the UAT preparation and review schedule:

  - 21/09: Sprint 3 Show & Tell covering CRM development.

  - 22/09: Share UAT test case coverage by role and begin account creation (22/09 – 02/10).

  - 06/10: Guided 4-hour UAT workshop at Fubon led by Deloitte (timeslots: 10:00–14:00 or 14:00–18:00, to be confirmed by Kay).

- [Kay]: Suggested combining next weekly meeting session and test case review into a single morning session on 25/09.

  - [Kay]: Confirmed CMG will reply regarding UAT workshop timing by Monday (21/09).

Change Management & Training

- [Steven]: Proposed scheduling a separate leadership meeting to review business goals, project adoption, and KPIs.

- [Kay]: Inquired about training plans.

  - [Steven]: Outlined training plan including introduction, documentation, and a 1-hour Teams session.

  - [Kay]: Requested two training sessions instead of one.

  - [Steven]:  Noted and will explore solution for running two training sessions.

- [Steven]: Requested nominating a Lead Champion to distribute surveys, define KPIs, and demonstrate CRM value.

  - [Kay]: Confirmed business leadership should define KPIs.

Action Items

- Windy – Reschedule the weekly on 25/09 to AM.

- Deloitte - Share UAT test case coverage by (22/09).

- Deloitte – Go through UAT Test Case Coverage on weekly. (25/09)

- Kay/ITG - Clarify and align on the owner for Account list / Call Target upload.

- Cindy – Follow up on the source of the renewal date and risk rating from Finacle.

- Windy - Schedule meeting with Group leader to discuss and set KPIs for Change Management.

- Kay – To confirm the timeslot of the UAT session on 06/10 (timeslots: 10:00–14:00 or 14:00–18:00).

- Windy – Collaborate with Kay for the actual timeslot and send meeting invites to the UAT Workshop and coordinate on the venue booking.

- Deloitte - Explore feasibility to offer two training sessions for CRM adoption.